## Bug Reports
E-COMMERCE WEBSITE — BUG / DEFECT REPORT LOG
Project: Online Shopping Platform (Web) ¦ Prepared By: Vikas ¦ Version: 1.0
Bug ID | Title | Module | Linked Test Case ID | Description | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Reported By | Date Reported
BUG_001 | Weak password accepted despite validation warning | User Registration | TC_REG_004 | System shows a password-strength error but still allows account creation with a weak password like '123' on second submit. | 1. Go to Registration page 2. Enter password '123' 3. Note validation error appears 4. Click Register again without changing password | Registration should be blocked until password meets policy (min 8 chars, letters+numbers) | Account gets created successfully with weak password on 2nd click | Major | High | Open | Chrome 125 / Windows 11 | Vikas | 03-Jul-2026
BUG_002 | No account lockout after repeated failed login attempts | User Login | TC_LGN_006 | Brute-force protection is not triggered even after 5 consecutive failed login attempts with wrong password. | 1. Go to Login page 2. Enter valid email with wrong password 3. Repeat 5 times consecutively | Account should lock for 15 minutes with message 'Too many attempts, try later' | Login form keeps accepting attempts indefinitely with no lockout or CAPTCHA | Critical | High | Open | Chrome 125 / Windows 11 | Vikas | 03-Jul-2026
BUG_003 | Blank white screen on search with special characters | Product Search & Filter | TC_SRC_003 | Searching with special characters like '@@##$$' causes the results page to render blank instead of a friendly no-results message. | 1. Go to Homepage search bar 2. Enter '@@##$$' 3. Press Enter | 'No results found' message should be shown to the user | Page goes blank white; console shows a JS rendering error | Major | Medium | Open | Chrome 125 / Windows 11 | Vikas | 03-Jul-2026
BUG_004 | Cart quantity not capped to available stock | Shopping Cart | TC_CRT_008 | Cart allows setting quantity beyond actual available stock without any warning, risking overselling. | 1. Add product with only 2 units in stock to cart 2. In cart, manually change quantity to 5 3. Observe cart total | System should cap quantity at 2 and show 'Only 2 units available' warning | Quantity of 5 is accepted silently; no stock validation performed | Major | High | In Progress | Chrome 125 / Windows 11 | Vikas | 04-Jul-2026
BUG_005 | Incorrect tax calculation on order summary | Checkout & Payment | TC_CHK_008 | Tax amount shown on the order review screen is off by ₹5 for products under the 'Electronics' category, causing final total mismatch. | 1. Add an Electronics category item worth ₹1800 to cart 2. Proceed to Checkout > Order Summary 3. Compare displayed tax vs expected (18% GST) | Tax should be calculated precisely as per applicable GST slab with no rounding discrepancy | Displayed tax is ₹5 less than the correct computed value | Major | High | Open | Chrome 125 / Windows 11 | Vikas | 04-Jul-2026
BUG_006 | Duplicate order created on rapid double-click of Pay Now | Checkout & Payment | TC_CHK_009 | Clicking the 'Pay Now' button twice in quick succession creates two separate orders and may cause duplicate payment capture. | 1. Reach payment step with valid card details 2. Double-click 'Pay Now' rapidly before page response | Only one order should be created; button should disable after first click to prevent resubmission | Two identical orders are created in Order History for a single checkout session | Critical | Critical | Open | Chrome 125 / Windows 11 | Vikas | 04-Jul-2026